## Revision Page
Rocket Sports Reservation System
Risk List
Date | Author(s) | Changes | Version
2020-02-29 | Didem Çetin | Initial Version | 1.0
2020-03-06 | Didem Çetin | -Update Risks according to QA team review | 2.0

## Risks
Rocket Sports Reservation System Risk List
Risk ID | Date Identified | Headline | Description | Type | Impact | Probability | Magnitude | Owner | Mitigation Strategy
1 | 2020-02-03 | Early leave of team members | Team members may leave company before the project finishes, and this can result in hiring new people and unexpected training costs. | Business | 4 | 20% | 0.8 | Didem Çetin | The ways to increse commitment of the project members will be analyzed.
2 | 2020-02-03 | Inaccurate size planning | The size of the project may be underestimated, so the cost of the project may increase. | Business | 5 | 10% | 0.5 | Didem Çetin | The project should be periodically tracked and analyzed and if the project size starts to increase than expected, other costs will be tried to decrase.
4 | [6 empty] | 0
5 | [6 empty] | 0
6 | [6 empty] | 0
7 | [6 empty] | 0
8 | [6 empty] | 0
9 | [6 empty] | 0
10 | [6 empty] | 0
11 | [6 empty] | 0
12 | [6 empty] | 0
13 | [6 empty] | 0
14 | [6 empty] | 0
15 | [6 empty] | 0
16 | [6 empty] | 0
17 | [6 empty] | 0