## Revision Page
Rocket Sports Reservation System
Work Items List
Date | Author(s) | Changes | Version
2020-02-29 | Didem Çetin Deniz Çoker Gülşah Kırtıloğlu Serçin Üstündağ | Initial Version | 1.0
2020-03-06 | Didem Çetin Deniz Çoker Gülşah Kırtıloğlu Serçin Üstündağ | -Update Work Items List according to QA team review | 2.0

## Sheet1
Name / Description | Priority | Size estimate (Points) | State | Target iteration | Assigned To | Effort estimate left (hours) | Hours worked | Reference material
Prepare Glossary V1 | 2 | 5 | Closed | 1 | Gülşah Kırtıloğlu | 0 | 2 | Detail System-Wide Requirements, Detail Use-Case Scenarios, Identify and Outline Requirements
Prepare Iteration-1 Plan | 1 | 8 | Closed | 0 | Didem Çetin | 0 | 5 | Iteration plan template, Iteration Burndown
Prepare Iteration-2 Plan | 1 | 8 | Closed | 1 | Didem Çetin | 0 | 5 | Iteration plan template, Iteration Burndown
Make Assesment for Iteration-1 | 1 | 1 | Closed | 1 | Deniz Çoker Didem Çetin Gülşah Kırtıloğlu Serçin Üstündağ | 0 | 2 | Iteration plan template, Iteration Burndown
Prepare Project Plan V1 | 1 | 7 | Closed | 1 | Deniz Çoker Didem Çetin Gülşah Kırtıloğlu | 0 | 10 | Project Plan template, Project Work, Technical Specification, Vision
Prepare Risk List V1 | 1 | 5 | Closed | 1 | Didem Çetin | 0 | 4 | Risk list template, assessments
Prepare System Wide Requirements V1 | 2 | 9 | Closed | 1 | Deniz Çoker Gülşah Kırtıloğlu Serçin Üstündağ | 0 | 15 | Customer needs, standard requirements
Prepare Fully Dressed Use Cases UC1- UC2-UC6 | 2 | 7 | Closed | 1 | Serçin Üstündağ | 0 | 15 | Detail Use-Case Scenarios, Customer needs
Prepare Use Case Model V1 | 2 | 8 | Closed | 1 | Serçin Üstündağ | 0 | 3 | Use Cases
Define Vision | 1 |  | Closed | 0 | Deniz Çoker Didem Çetin Gülşah Kırtıloğlu Serçin Üstündağ | 0 | 8 | Vision template
Update Vision | 1 | 10 | Closed | 1 | Deniz Çoker | 0 | 8 | First version Vision
Prepare Work Item List V1 | 1 | 8 | Closed | 1 | Deniz Çoker Didem Çetin Gülşah Kırtıloğlu Serçin Üstündağ | 0 | 10 | Assessments, Requirements, Iteration Plan
Prepare Design and Architecture Notebook | 1 | 8 | Start | 2 | Deniz Çoker Didem Çetin Gülşah Kırtıloğlu Serçin Üstündağ | 12 | 0 | Use cases, use case models, System Wide Requirements
Update Glossary V2 | 2 | 3 | In Progress | 2 | Deniz Çoker | 2 | 0 | Detail System-Wide Requirements, Detail Use-Case Scenarios, Identify and Outline Requirements, Defined Glossary
Implementation UC1 ,UC2 and UC6 | 1 | 9 | Start | 2 | Deniz Çoker Gülşah Kırtıloğlu | 24 | 0 | Use cases, use case models, System Wide Requirements
Prepare Iteration-3 Plan | 1 | 2 | Start | 2 | Didem Çetin | 8 | 0 | Iteration plan template, Iteration Burndown
Make Assesment for Iteration-2 | 2 | 2 | Assigned | 2 | Deniz Çoker Serçin Üstündağ | 2 | 0 | Iteration plan template, Iteration Burndown
Update Project Plan V2 | 2 | 4 | In Progress | 2 | Didem Çetin | 10 | 0 | Project Plan, Project Work, Technical Specification, Vision
Update Risk List | 1 | 2 | In Progress | 2 | Didem Çetin | 4 | 0 | Risk list template, assessments
Update Vision V2 | 2 | 1 | In Progress | 2 | Deniz Çoker | 8 | 0 | Prepared Vision
Prepare Tools | 2 | 2 | Assigned | 2 | Deniz Çoker Gülşah Kırtıloğlu | 3 | 0
Update Use Cases V2 | 1 | 7 | In Progress | 2 | Serçin Üstündağ | 7 | 0 | Detail Use-Case Scenarios, Customer needs
Update Work Item List V2 | 1 | 6 | In Progress | 2 | Didem Çetin | 10 | 0
Prepare Test Cases For UC1 and UC2 | 2 | 8 | Start | 2 | Didem Çetin Serçin Üstündağ | 10 | 0 | Use cases, use case models, System Wide Requirements
Prepare System Wide Requirements V2 | 1 | 8 | In Progress | 2 | Deniz Çoker Gülşah Kırtıloğlu Serçin Üstündağ | 15 | 0 | Customer needs, standard requirements
Update Use Case Model V2 | 1 | 4 | In Progress | 2 | Serçin Üstündağ | 3 | 0 | Use Cases

## Sheet2
Name / Description | Priority | Size estimate (Points) | State | Target iteration | Assig-ned To | Effort estimate left (hours) | Hours worked | Reference material
Architecture Notebook |  |  |  |  | Architect |  |  | Architecture Notebook Template
Product Documentation |  |  |  |  | Technical Writer
Support Documentation |  |  |  |  | Technical Writer |  |  | User manuals with work instructions, process descriptions, and procedures, Communications, training, and knowledge transfer deliverables, Support and operations manuals, Service information, including Help Desk scripts
User Documentation |  |  |  |  | Technical Writer |  |  | Tutorials, frequently asked questions (FAQs), on-line Help Files, installation instructions, work instructions, operational procedures
Training Materials |  |  |  |  | Course Developer
Backout Plan |  |  |  |  | Deployment Engineer
Deployment Plan |  |  |  |  | Deployment Engineer |  |  | Unique instructions for deploying a particular version of a product
Infrastructure |  |  |  |  | -
Release Communications |  |  |  |  | Deployment Engineer
Release Controls |  |  |  |  | Deployment Manager
Release |  |  |  |  | Deployment Engineer
Implementation |  |  |  |  | Developer |  |  | Source code files, Data files, Build scripts, Other files that are transformed into the executable system
Build |  |  |  |  | Developer
Developer Test |  |  |  |  | Developer |  |  | Setup Inputs, Script, Expected Results ,Evaluation Criteria, Clean-Up
Design |  |  |  |  | Developer
Project Defined Process |  |  |  |  | Process Engineer |  |  | Development Case for a Project
Tools |  |  |  |  | Project Manager
Risk List |  |  |  |  | Project Manager
Work Items List |  |  |  |  | Project Manager
Iteration Plan |  |  |  |  | Project Manager
Project Plan |  |  |  |  | Project Manager
Glossary |  |  |  |  | Analyst
Vision |  |  |  |  | Analyst
System-Wide Requirements |  |  |  |  | Analyst